## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2022-11-01 | 2022-11-02 | 2022-11-03 | 2022-11-04 | 2022-11-05 | 2022-11-06 | 2022-11-07 | 2022-11-08
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8
1 | Create User Stories | 0.5
2 | Implement task filter funcionality | 15
3 | Implement multiple tasks editing funcionality | 15
4 | Create Unit Tests | 5
5 | Record new funcionalities demonstration video | 1
6 | Create Use Cases | 10
7 | Codebase metrics assessment | 10
Completed Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining Effort |  | 56.5 | 56.5 | 56.5 | 56.5 | 56.5 | 56.5 | 56.5 | 56.5 | 56.5
Ideal Burndown |  | 56.5 | 49.4375 | 42.375 | 35.3125 | 28.25 | 21.1875 | 14.125 | 7.0625 | 0
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8