## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2022-10-22 | 2022-10-23 | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 2022-10-29 | 2022-10-30
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9
1 | Create User Stories | 0.5
2 | Implement task filter funcionality | 15
3 | Implement multiple tasks editing funcionality | 15
4 | Create Unit Tests | 5
5 | Record new funcionalities demonstration video | 1
6 | Create Use Case Diagrams (Assigned to Ana) | 2
7 | Create Use Case Diagrams (Assigned to Joana) | 2
8 | Create Use Case Diagrams (Assigned to Nelson) | 2
9 | Create Use Case Diagrams (Assigned to Pedro) | 2
10 | Create Use Case Diagrams (Assigned to Renato) | 2
11 | Create Use Cases Descriptions (Assigned to Ana) | 2
12 | Create Use Cases Descriptions (Assigned to Joana) | 2
13 | Create Use Cases Descriptions (Assigned to Nelson) | 2
14 | Create Use Cases Descriptions (Assigned to Pedro) | 2
15 | Create Use Cases Descriptions (Assigned to Renato) | 2
16 | Codebase metrics assessment (Assigned to Ana) | 2
17 | Codebase metrics assessment (Assigned to Joana) | 2
18 | Codebase metrics assessment (Assigned to Nelson) | 2
19 | Codebase metrics assessment (Assigned to Pedro) | 2
20 | Codebase metrics assessment (Assigned to Renato) | 2
Completed Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining Effort |  | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5 | 66.5
Ideal Burndown |  | 66.5 | 59.1111 | 51.7222 | 44.3333 | 36.9444 | 29.5556 | 22.1667 | 14.7778 | 7.3889 | 0
Nota: a equipa esteve ocupada com outros projetos nesta semana, por isso não foi possível progredir significativamente neste projeto.