## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-12 | 2022-11-13 | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-17
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9
1 | Create User Stories | 0.5
2 | Implement task filter funcionality | 15
3 | Implement multiple tasks editing funcionality | 15
4 | Create Unit Tests | 5
5 | Record new funcionalities demonstration video | 1
6 | Create Use Cases | 10
7 | Codebase metrics assessment | 10
Completed Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining Effort |  | 56.5 | 56.5 | 56.5 | 56.5 | 56.5 | 56.5 | 56.5 | 56.5 | 56.5 | 56.5
Ideal Burndown |  | 56.5 | 50.2222 | 43.9444 | 37.6667 | 31.3889 | 25.1111 | 18.8333 | 12.5556 | 6.2778 | 0