## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2022-10-22 | 2022-10-23 | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 2022-10-29 | 2022-10-30
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9
1 | Create User Stories | 0.5
2 | Implement task filter funcionality | 15
3 | Implement multiple tasks editing funcionality | 15
4 | Create Unit Tests | 5
5 | Record new funcionalities demonstration video | 1
6 | Create Use Cases | 10
7 | Codebase metrics assessment | 10
Completed Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining Effort |  | 56.5 | 56.5 | 56.5 | 56.5 | 56.5 | 56.5 | 56.5 | 56.5 | 56.5 | 56.5
Ideal Burndown |  | 56.5 | 50.2222 | 43.9444 | 37.6667 | 31.3889 | 25.1111 | 18.8333 | 12.5556 | 6.2778 | 0